## Dwgs-Out
MAJURO GENERATING STATION NO.2
[5 empty] | DISTRIBUTION DETAILS | STATUS |  |  | ISSUED FOR
OUTWARD DRAWING REGISTER |  |  | T = Transparency |  |  | L = Latest |  |  | P = Preliminary |  |  |  |  | O = Ordering
|  |  | A = A1 print |  |  | S = Superseded |  |  | I = Information |  |  |  |  | B = Building Consent
WORLEY CONSULTANTS LTD |  |  | B = B print |  |  | W = Withdrawn |  |  | R = Review |  |  |  |  | C = Construction
|  |  | D = 3½" disk |  | C = A4 print
Job No 22.404.24 |  |  | E = Email |  | F = Fax |  |  | Distribution
| Dwg No. | Drawing Title | Rev | Format | Date of Issue | Status | Issued for | McConnel Dowell | McDow site | Deutz Australia | MBT | Hegley Accoustic C | McDow Australia | Oceanic Co. Inc | JOTT Australia
Civil/Structural | [5 empty] | L
| 001 | General Notes and Drawing Index | 2 |  |  | S
| 001 | General Notes and Drawing Index | 3 | dwg | 1998-04-14 | S | I | A
| 001 | General Notes and Drawing Index | 4 | dwg | 1998-05-01 | S | I | A | E | E
| 001 | General Notes and Drawing Index | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 001 | General Notes and Drawing Index | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E
| 001 | General Notes and Drawing Index | C | dwg | 1998-06-05 | S | C | AB | [5 empty] | E
| 001 | General Notes and Drawing Index | C | dwg | 1998-07-17 | S | C | [7 empty] | E
| 001 | General Notes and Drawing Index | D | dwg | 1998-08-14 | L | C | AB | E | [5 empty] | E
| 002 | Locality and Site Plans | 1 |  |  | S
| 002 | Locality and Site Plans | 2 | dwg | 1998-04-14 | S | I | A
| 002 | Locality and Site Plans | 3 | dwg | 1998-05-01 | S | I | A | E | E
| 002 | Locality and Site Plans | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 002 | Locality and Site Plans | B | dwg | 1998-05-14 | S | C | A |  |  |  |  | E | E
| 002 | Locality and Site Plans | B | dwg | 1998-07-17 | S | C | [7 empty] | E
| 002 | Locality and Site Plans | C | dwg | 1998-08-14 | L | C | AB | E | [5 empty] | E
| 003 | Fencing Details | 1 |  |  | S
| 003 | Fencing Details | 2 | dwg | 1998-04-14 | S | I | A
| 003 | Fencing Details | 3 | dwg | 1998-05-01 | S | I | A | E | E
| 003 | Fencing Details | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E | E
| 003 | Fencing Details | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 003 | Fencing Details | B | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 201 | Trench Details and Foundation Plan | 2 | bar: S
| 201 | Trench Details and Foundation Plan | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 201 | Trench Details and Foundation Plan | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 201 | Trench Details and Foundation Plan | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 201 | Trench Details and Foundation Plan | B | dwg | 1998-05-14 | S: S; C: C; A: A; E: E
| 201 | Trench Details and Foundation Plan | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 201 | Trench Details and Foundation Plan | D | dwg | 1998-06-30 | S: S; C: C; A: AB; E: E; E: E
| 201 | Trench Details and Foundation Plan | E | dwg | 1998-07-17 | S: S; C: C; A: AB; E: E; E: E | E
| 201 | Trench Details and Foundation Plan | F | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 202 | Floor Plan | 2 | bar: S
| 202 | Floor Plan | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 202 | Floor Plan | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 202 | Floor Plan | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 202 | Floor Plan | B | dwg | 1998-05-14 | S: S; C: C; A: A; E: E
| 202 | Floor Plan | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 202 | Floor Plan | D | dwg | 1998-06-30 | S: S; C: C; A: AB; E: E; E: E
| 202 | Floor Plan | E | dwg | 1998-07-17 | S: S; C: C; A: AB; E: E; E: E | E
| 202 | Floor Plan | F | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 203 | Northern Part Floor Plan | 2 | bar: S
| 203 | Northern Part Floor Plan | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 203 | Northern Part Floor Plan | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 203 | Northern Part Floor Plan | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 203 | Northern Part Floor Plan | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E |  |  | Prelim copy issued McDow 15/5
| 203 | Northern Part Floor Plan | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E |  | Prelim copy issued McDow 15/5
| 203 | Northern Part Floor Plan | D | dwg | 1998-06-30 | S: S; C: C; A: AB; E: E; E: E
| 203 | Northern Part Floor Plan | E | dwg | 1998-07-17 | S: S; C: C; A: AB; E: E; E: E | E
| 203 | Northern Part Floor Plan | F | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 204 | Southern Part Floor Plan | 2 | bar: S
| 204 | Southern Part Floor Plan | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 204 | Southern Part Floor Plan | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 204 | Southern Part Floor Plan | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E | E
| 204 | Southern Part Floor Plan | B | dwg | 1998-05-06 | S: S; C: C; A: AB; E: E; E: E
| 204 | Southern Part Floor Plan | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 204 | Southern Part Floor Plan | C | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 211 | Foundations / Slab Details Sheet 1 | 2 | bar: S
| 211 | Foundations / Slab Details Sheet 1 | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 211 | Foundations / Slab Details Sheet 1 | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 211 | Foundations / Slab Details Sheet 1 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 211 | Foundations / Slab Details Sheet 1 | B | dwg | 1998-05-14 | S: S; C: C; A: A; E: E
| 211 | Foundations / Slab Details Sheet 1 | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 211 | Foundations / Slab Details Sheet 1 | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 212 | Foundations / Slab Details Sheet 2 | 1 | dwg | bar: S
| 212 | Foundations / Slab Details Sheet 2 | 2 | dwg | 1998-04-14 | S: S; C: I; A: A
| 212 | Foundations / Slab Details Sheet 2 | 3 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 212 | Foundations / Slab Details Sheet 2 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 212 | Foundations / Slab Details Sheet 2 | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E |  |  | Prelim copy issued McDow 15/5
| 212 | Foundations / Slab Details Sheet 2 | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E |  | Prelim copy issued McDow 15/5
| 212 | Foundations / Slab Details Sheet 2 | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 212 | Foundations / Slab Details Sheet 2 | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 221 | Roof Plans | 3 | dwg | bar: S
| 221 | Roof Plans | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 221 | Roof Plans | 5 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 221 | Roof Plans | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 221 | Roof Plans | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E |  |  | Prelim copy issued McDow 15/5
| 221 | Roof Plans | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E |  | Prelim copy issued McDow 15/5
| 221 | Roof Plans | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 221 | Roof Plans | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 222 | Elevation Grid A | 3 | dwg | bar: S
| 222 | Elevation Grid A | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 222 | Elevation Grid A | 5 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 222 | Elevation Grid A | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 222 | Elevation Grid A | B | dwg | 1998-05-14 | S: L; C: C; A: A; E: E; E: E
| 222 | Elevation Grid A | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 223 | Section Grid B | 3 | dwg | bar: S
| 223 | Section Grid B | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 223 | Section Grid B | 5 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 223 | Section Grid B | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E
| 223 | Section Grid B | B | dwg | 1998-05-22 | S: S; C: C; A: AB
| 223 | Section Grid B | C | dwg | 1998-06-05 | S: S; C: C; A: AB | E
| 223 | Section Grid B | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 223 | Section Grid B | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E |  | E
| 224 | Section Grid C | 3 | dwg | bar: S
| 224 | Section Grid C | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 224 | Section Grid C | 5 | dwg | 1998-05-01 | S | I | A | E | E
| 224 | Section Grid C | A | dwg | 1998-05-06 | L | C | A | E | E | B | B | E | E
| 224 | Section Grid C | A | dwg | 1998-07-17 | [9 empty] | E | bar: L to C
| 225 | Elevation Grid D & E | 3 | dwg | bar: L
| 225 | Elevation Grid D & E | 4 | dwg | 1998-04-14 | L: S; C: I; A: A
| 225 | Elevation Grid D & E | 5 | dwg | 1998-05-01 | L: S; C: I; A: A; E: E; E: E
| 225 | Elevation Grid D & E | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 225 | Elevation Grid D & E | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E
| 225 | Elevation Grid D & E | C | dwg | 1998-06-05 | L: S; C: C; A: AB; E: E
| 225 | Elevation Grid D & E | C | dwg | 1998-07-17 | [9 empty] | E | bar: L to C
| 225 | Elevation Grid D & E | D | dwg | 1998-08-14 | L: L; C: C; A: AB; E: E | E
| 226 | Elevation Grid 1 | 3 | dwg | bar: L
| 226 | Elevation Grid 1 | 4 | dwg | 1998-04-14 | L: S; C: I; A: A
| 226 | Elevation Grid 1 | 5 | dwg | 1998-05-01 | L: S; C: I; A: A; E: E; E: E
| 226 | Elevation Grid 1 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E
| 226 | Elevation Grid 1 | B | dwg | [9 empty] | E | bar: S to C
| 226 | Elevation Grid 1 | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 226 | Elevation Grid 1 | C | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E |  | E
| 227 | Elevation Grid 3 & 4 | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 227 | Elevation Grid 3 & 4 | 5 | dwg | 1998-05-01 | S | I | A | E | E
| 227 | Elevation Grid 3 & 4 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 227 | Elevation Grid 3 & 4 | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E | E |  | Prelim copy issued McDow 15/5
| 227 | Elevation Grid 3 & 4 | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 227 | Elevation Grid 3 & 4 | C | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E |  | E
| 231 | Structural Details Sheet 1 | 2 | dwg | bar: S
| 231 | Structural Details Sheet 1 | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 231 | Structural Details Sheet 1 | 4 | dwg | 1998-05-01 | S | I | A | E | E
| 231 | Structural Details Sheet 1 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E
| 231 | Structural Details Sheet 1 | B | dwg | 1998-06-05 | S: L; C: C; A: AB | E
| 231 | Structural Details Sheet 1 | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 232 | Structural Details Sheet 2 | 1 | dwg | bar: S
| 232 | Structural Details Sheet 2 | 2 | dwg | 1998-04-14 | S: S; C: I; A: A
| 232 | Structural Details Sheet 2 | 3 | dwg | 1998-05-01 | S | I | A | E | E
| 232 | Structural Details Sheet 2 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B | E | E
| 232 | Structural Details Sheet 2 | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 232 | Structural Details Sheet 2 | B | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 233 | Structural Details Sheet 3 | 2 | dwg | bar: S
| 233 | Structural Details Sheet 3 | 3 | dwg | 1998-04-14 | S: S; C: I; A: A
| 233 | Structural Details Sheet 3 | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 233 | Structural Details Sheet 3 | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 233 | Structural Details Sheet 3 | B | dwg | 1998-05-06 | S: S; C: C; A: A; E: E; E: E
| 233 | Structural Details Sheet 3 | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 233 | Structural Details Sheet 3 | C | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 241 | Precast Concrete Panel Joint Details | 3 | dwg | bar: S
| 241 | Precast Concrete Panel Joint Details | 4 | dwg | 1998-04-14 | S: S; C: I; A: A
| 241 | Precast Concrete Panel Joint Details | 5 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 241 | Precast Concrete Panel Joint Details | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 241 | Precast Concrete Panel Joint Details | B | dwg | 1998-05-19 | L | C | AB | E | E |  |  | E | E
| 241 | Precast Concrete Panel Joint Details | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 242 | P/C Panels Standard Cross Sections | 1 | dwg | bar: S
| 242 | P/C Panels Standard Cross Sections | 2 | dwg | 1998-04-14 | S: S; C: I; A: A
| 242 | P/C Panels Standard Cross Sections | 3 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 242 | P/C Panels Standard Cross Sections | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 242 | P/C Panels Standard Cross Sections | B | dwg | 1998-05-14 | S: S; C: C; A: A; E: E
| 242 | P/C Panels Standard Cross Sections | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 242 | P/C Panels Standard Cross Sections | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 242 | P/C Panels Standard Cross Sections | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 243 | P/C Roof Panels Standard Cross Sections | 1 | dwg | bar: S
| 243 | P/C Roof Panels Standard Cross Sections | 2 | dwg | 1998-04-14 | S: S; C: I; A: A
| 243 | P/C Roof Panels Standard Cross Sections | 3 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 243 | P/C Roof Panels Standard Cross Sections | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 243 | P/C Roof Panels Standard Cross Sections | B | dwg | 1998-05-14 | S: S; C: C; A: A; E: E
| 243 | P/C Roof Panels Standard Cross Sections | C | dwg | 1998-06-05 | S: L; C: C; A: AB; E: E
| 243 | P/C Roof Panels Standard Cross Sections | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 251 | Miscellaneous Details | 1 | dwg | bar: S
| 251 | Miscellaneous Details | 2 | dwg | 1998-04-14 | S: S; C: I; A: A
| 251 | Miscellaneous Details | 3 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 251 | Miscellaneous Details | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 251 | Miscellaneous Details | B | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E
| 251 | Miscellaneous Details | C | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 251 | Miscellaneous Details | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 251 | Miscellaneous Details | D | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 252 | Ladder details | A | dwg | 1998-05-20 | S: S; C: C; A: AB
| 252 | Ladder details | B | dwg | 1998-06-05 | S: L; C: C; A: AB; E: E
| 253 | Outside Platform By Grid 1 | 1 | dwg | 1998-05-12 | S: S; C: R; A: A
| 253 | Outside Platform By Grid 1 | A | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E | E
| 253 | Outside Platform By Grid 1 | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 253 | Outside Platform By Grid 1 | B | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 254 | Day Tank Steps | 1 | dwg | 1998-05-14 | S: S; C: R; A: AB
| 254 | Day Tank Steps | A | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E | E
| 254 | Day Tank Steps | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 254 | Day Tank Steps | B | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 255 | Generator Hall Main Door | 1 | dwg | 1998-05-12 | S: S; C: R; A: A
| 255 | Generator Hall Main Door | A | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E
| 255 | Generator Hall Main Door | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 255 | Generator Hall Main Door | B | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 256 | External Stairs By Grid 4 | 1 | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
| 261 | Switching Station Plan & Details | 1 | dwg | 1998-05-14 | S: S; C: R; A: AB
| 261 | Switching Station Plan & Details | A | dwg | 1998-05-19 | S | C | AB | E | E |  |  | E | E
| 261 | Switching Station Plan & Details | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 261 | Switching Station Plan & Details | B | dwg | 1998-08-14 | S: L; C: C; A: AB; E: E | E
L
Architectural | bar: S; E
| 301 | Floor Plan | 2 | dwg | bar: S
| 301 | Floor Plan | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 301 | Floor Plan | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 301 | Floor Plan | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 301 | Floor Plan | B | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 301 | Floor Plan | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 301 | Floor Plan | C | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| 302 | Elevations | 2 | dwg | bar: S
| 302 | Elevations | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 302 | Elevations | 4 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 302 | Elevations | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 302 | Elevations | B | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 302 | Elevations | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 302 | Elevations | C | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| 303 | Sections | 2 | dwg | bar: S
| 303 | Sections | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 303 | Sections | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 303 | Sections | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 303 | Sections | B | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 303 | Sections | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 303 | Sections | C | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | 1 | dwg | bar: S
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | 3 | dwg | 1998-05-01 | S: S; C: I; A: A; E: E; E: E
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | A | dwg | 1998-05-06 | S | C | A | E | E | B | B
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | B | dwg | 1998-06-05 | S: S; C: C; A: AB; E: E
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 304 | Plumbing & Drainage Toilet Elevations Door & Window Schedules | C | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| 305 | Door Details Gutter Details | 1 | dwg | bar: S
| 305 | Door Details Gutter Details | A | dwg | 1998-04-14 | S: S; C: I; A: A
| 305 | Door Details Gutter Details | A | dwg | 1998-05-06 | S | C | A | E | E | B | B |  | E
| 305 | Door Details Gutter Details | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 305 | Door Details Gutter Details | B | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| 306 | Details | A | dwg | 1998-06-12 | S: S; C: C; A: AB; E: E
| 306 | Details | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| 306 | Details | B | dwg | 1998-08-17 | S: L; C: C; A: AB; E: E | E
L
Building Services | bar: S; E
| M100 | Power House Ventilation | 1 | dwg | 1998-05-07 | S: S; C: P; A: B
| M100 | Power House Ventilation | A | dwg | 1998-05-21 | S: S; C: C; A: AB
| M100 | Power House Ventilation | B | dwg | 1998-06-15 | S: L; C: C; A: AB; E: E
| M100 | Power House Ventilation | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| M101 | Control Room & Service Area HVAC Layout | A | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| M101 | Control Room & Service Area HVAC Layout | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| M102 | Compressed Air System | 1 | dwg | 1998-05-07 | S: S; C: P; A: B
| M102 | Compressed Air System | A | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| M102 | Compressed Air System | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| M200 | HW-CW Layout & Schematic | 0 | dwg | 1998-05-07 | S: S; C: P; A: B
| M200 | HW-CW Layout & Schematic | A | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| M200 | HW-CW Layout & Schematic | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| M201 | Mechanical Services Air Conditioning Equipment Schedule | 1 | dwg | 1998-05-07 | S: S; C: P; A: B
| M201 | Mechanical Services Air Conditioning Equipment Schedule | A | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| M201 | Mechanical Services Air Conditioning Equipment Schedule | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| E501 | Electrical Services External Lighting Layout | A | dwg | 1998-04-29 | S: S; C: P; A: B
| E501 | Electrical Services External Lighting Layout | B | dwg | 1998-05-21 | S: S; C: C; A: AB
| E501 | Electrical Services External Lighting Layout | C | dwg | 1998-06-05 | S: L; C: C; A: AB; E: E
| E501 | Electrical Services External Lighting Layout | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| E502 | Electrical Services Lighting Layout | A | dwg | 1998-04-29 | S: S; C: P; A: B
| E502 | Electrical Services Lighting Layout | B | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| E502 | Electrical Services Lighting Layout | B | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| E503 | Electrical Services Power Layout | A | dwg | 1998-04-29 | S: S; C: P; A: B
| E503 | Electrical Services Power Layout | B | dwg | 1998-05-21 | S: S; C: C; A: AB
| E503 | Electrical Services Power Layout | C | dwg | 1998-06-05 | S: L; C: C; E: E
| E503 | Electrical Services Power Layout | C | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
| F101 | Fire Services Layout | A | dwg | 1998-05-21 | S: L; C: C; A: AB; E: E
| F101 | Fire Services Layout | A | dwg | 1998-07-17 | [9 empty] | E | bar: S to C
Specifications | bar: S
| MG100 | Preliminaries and General | 1 | doc | 1998-05-13 | S: L; C: R; A: CD; E: E
| MG101 | Site Clearance | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG101 | Site Clearance | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG101 | Site Clearance | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG101 | Site Clearance | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG101 | Site Clearance | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG102 | Excavation | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG102 | Excavation | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG102 | Excavation | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG102 | Excavation | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG102 | Excavation | E | doc | 1998-05-13 | S: S; C: C; A: CD
| MG102 | Excavation | E | doc | 1998-05-13 | bar: S to A
| MG102 | Excavation | F | doc | 1998-05-21 | bar: S to A
| MG102 | Excavation | G | doc | 1998-05-26 | S: L; C: C; A: CE; E: E
| MG103 | Filling | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG103 | Filling | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG103 | Filling | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG103 | Filling | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG103 | Filling | E | doc | 1998-05-13 | S: S; C: C; A: CD
| MG103 | Filling | E | doc | 1998-05-13 | bar: S to A
| MG103 | Filling | F | doc | 1998-05-21 | S: L; C: C; A: C; E: E
| MG104 | Formwork | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG104 | Formwork | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG104 | Formwork | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG104 | Formwork | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG104 | Formwork | E | doc | 1998-05-13 | bar: S to A
| MG104 | Formwork | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG105 | Reinforcement | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG105 | Reinforcement | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG105 | Reinforcement | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG105 | Reinforcement | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG105 | Reinforcement | E | doc | 1998-05-13 | bar: S to A
| MG105 | Reinforcement | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG106 | Concrete Production | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG106 | Concrete Production | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG106 | Concrete Production | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG106 | Concrete Production | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG106 | Concrete Production | D | doc | 1998-05-13 | bar: S to A
| MG106 | Concrete Production | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG107 | Concrete Placement | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG107 | Concrete Placement | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG107 | Concrete Placement | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG107 | Concrete Placement | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG107 | Concrete Placement | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG108 | Precast Concrete Cladding | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG108 | Precast Concrete Cladding | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG108 | Precast Concrete Panels | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG108 | Precast Concrete Panels | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG108 | Precast Concrete Panels | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG109 | Concrete Finishes and Tolerances | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG109 | Concrete Finishes and Tolerances | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG109 | Concrete Finishes and Tolerances | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG109 | Concrete Finishes and Tolerances | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG109 | Concrete Finishes and Tolerances | E | doc | 1998-05-13 | bar: S to A
| MG109 | Concrete Finishes and Tolerances | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG110 | Concrete Masonry | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG110 | Concrete Masonry | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG110 | Concrete Masonry | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG110 | Concrete Masonry | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG110 | Concrete Masonry | E | doc | 1998-05-13 | bar: S to A
| MG110 | Concrete Masonry | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG111 | Structural Steel | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG111 | Structural Steel | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG111 | Structural Steel | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG111 | Structural Steel | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG111 | Structural Steel | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG112 | Drainage | A | doc | 1998-02-13 | S: S; C: R; A: C
| MG112 | Drainage | B | doc | 1998-03-16 | S: S; C: R; A: C
| MG112 | Drainage | C | doc | 1998-04-14 | S: S; C: R; A: C
| MG112 | Drainage | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG112 | Drainage | E | doc | 1998-05-13 | S: S; C: C; A: CD
| MG112 | Drainage | F | doc | 1998-05-27 | S: L; C: C; A: CE; E: E
| MG201 | Light Timber Framing | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG201 | Light Timber Framing | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG201 | Light Timber Framing | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG202 | Rainwater Pipework/Gutters | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG202 | Rainwater Pipework/Gutters | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG202 | Rainwater Pipework/Gutters | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG203 | Specialist Coatings | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG203 | Specialist Coatings | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG203 | Specialist Coatings | E | doc | 1998-05-13 | bar: S to A
| MG203 | Specialist Coatings | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG204 | Painting Preparation | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG204 | Painting Preparation | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG204 | Painting Preparation | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG205 | Painting/Clear Finishing | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG205 | Painting/Clear Finishing | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG205 | Painting/Clear Finishing | E | doc | 1998-05-13 | bar: S to A
| MG205 | Painting/Clear Finishing | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG206 | Hot and Cold Water Supply | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG206 | Hot and Cold Water Supply | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG206 | Hot and Cold Water Supply | E | doc | 1998-05-13 | S: L; C: C; A: CD; E: E
| MG207 | Sanitary Fixtures | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG207 | Sanitary Fixtures | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG207 | Sanitary Fixtures | E | doc | 1998-05-13 | bar: S to A
| MG207 | Sanitary Fixtures | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG208 | Sanitary Plumbing | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG208 | Sanitary Plumbing | D | doc | 1998-05-05 | S: S; C: R; A: CD
| MG208 | Sanitary Plumbing | E | doc | 1998-05-13 | S: L; C: C; A: C; E: E
| MG209 | Plasterboard Linings | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG209 | Plasterboard Linings | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG209 | Plasterboard Linings | E | doc | 1998-05-13 | bar: S to A
| MG209 | Plasterboard Linings | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG210 | Vinyl Flooring | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG210 | Vinyl Flooring | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG210 | Vinyl Flooring | E | doc | 1998-05-13 | bar: S to A
| MG210 | Vinyl Flooring | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG211 | Ceramic Tile Flooring | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG211 | Ceramic Tile Flooring | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG211 | Ceramic Tile Flooring | E | doc | 1998-05-13 | bar: S to A
| MG211 | Ceramic Tile Flooring | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG212 | Suspended Ceilings | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG212 | Suspended Ceilings | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG212 | Suspended Ceilings | E | doc | 1998-05-13 | bar: S to A
| MG212 | Suspended Ceilings | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG213 | Aluminium Windows/Doors | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG213 | Aluminium Windows/Doors | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG213 | Aluminium Windows/Doors | E | doc | 1998-05-13 | bar: S to A
| MG213 | Aluminium Windows/Doors | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG214 | WC Partitions | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG214 | WC Partitions | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG214 | WC Partitions | E | doc | 1998-05-13 | bar: S to A
| MG214 | WC Partitions | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG215 | Doorsets | B | doc | 1998-04-14 | S: S; C: R; A: C
| MG215 | Doorsets | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG215 | Doorsets | E | doc | 1998-05-13 | bar: S to A
| MG215 | Doorsets | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG216 | Hardware | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG216 | Hardware | D | doc | 1998-05-05 | S: S; C: R; A: C
| MG216 | Hardware | E | doc | 1998-05-13 | bar: S to A
| MG216 | Hardware | F | doc | 1998-05-18 | S: L; C: C; A: CD; E: E
| MG217 | Door Schedule | A | doc | 1998-04-14 | S: S; C: R; A: C
| MG217 | Door Schedule | D | doc | 1998-05-05 | S: S; C: R; A: CD; E: E
| MG217 | Door Schedule | E | doc | 1998-08-17 | S: L; C: C; A: AB; E: E | E
| MG301 | Small Power & Lighting | A | doc | 1998-05-19 | S: L; C: R; E: E
| MG401 | Mechanical Building Services | A | doc | 1998-05-18 | S: L; C: R; E: E
| MG501 | Fire Detection & Protection | A | doc | 1998-05-20 | S: L; C: R; E: E